## Sheet1
Summary of Temporary Signalization and Detection - 443913-1-52-01
Section | Pay Item Number | Label | Pay Item Description | Max. Maint. Size | Structure Type | Structure Usage | Unit of Measure | Work Zone Speed (MPH) | Test Level (TL-2 or TL-3) | Existing (E) or Temp/New (T) | Number Required | Duration (Days) | Frequency (Days) | Length (FT) | Length Restriction (FT) | Width (FT) | Width of Barrier (IN) | Width of Hazard (IN) | Thickness (IN) | Cycles | Quantity |  |  | Total Quantity |  | Secondary Quantity |  |  | Location | [9 empty] | Design Notes | Construction Remarks
[21 empty] | AC/ Cycle | P | F | P | F | Unit | P | F | Const. Phase | Wall No. | Site No. | Alignment | Begin Station | End Station | Location Description | Offset | Side | Element ID
| 102 104 |  | TEMPORARY SIGNALIZATION AND MAINTENANCE, INTERSECTION |  |  |  | ED |  |  | E | 3 | 90 | [9 empty] | 270 |  | 810 |  |  |  |  | 1 | [9 empty] | 3 Intersections at 270 Construction Days
[10 empty] | E | 3 | 45 | [9 empty] | 135 | [6 empty] | 2
[10 empty] | E | 3 | 45 | [9 empty] | 135 | [6 empty] | 3
[10 empty] | E | 3 | 90 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 270 | [6 empty] | 4
| 102 107 1 |  | TEMPORARY TRAFFIC DETECTION AND MAINTENANCE, INTERSECTION |  |  |  | ED |  |  | E | 3 | 90 | [9 empty] | 270 |  | 810 |  |  |  |  | 1 | [9 empty] | 3 Intersections at 270 Construction Days
[10 empty] | E | 3 | 45 | [9 empty] | 135 | [6 empty] | 2
[10 empty] | E | 3 | 45 | [9 empty] | 135 | [6 empty] | 3
[10 empty] | E | 3 | 90 | [9 empty] | 270 | [6 empty] | 4