## Sheet1
Summary of Temporary Traffic Control Plan Items - 443913-1-52-01
Section | Pay Item Number | Label | Pay Item Description | Max. Maint. Size | Structure Type | Structure Usage | Unit of Measure | Work Zone Speed (MPH) | Test Level (TL-2 or TL-3) | Existing (E) or Temp/New (T) | Number Required | Duration (Days) | Frequency (Days) | Length (FT) | Length Restriction (FT) | Width (FT) | Width of Barrier (IN) | Width of Hazard (IN) | Thickness (IN) | Cycles | Quantity |  |  | Total Quantity |  | Secondary Quantity |  |  | Location | [9 empty] | Design Notes | Construction Remarks
[21 empty] | AC/ Cycle | P | F | P | F | Unit | P | F | Const. Phase | Wall No. | Site No. | Alignment | Begin Station | End Station | Location Description | Offset | Side | Element ID
| 0102 1 |  | MAINTENANCE OF TRAFFIC |  |  |  | LS | [14 empty] | 1 |  | 1 |  | DA | 270 |  | ALL | [9 empty] | ASSUMED 270 CONSTRUCTION DAYS
| 0102 14 |  | TRAFFIC CONTROL OFFICER |  |  |  | HR |  |  |  | 4 | 23 | [9 empty] | 368 |  | 1036 |  |  |  |  | 1 | [9 empty] | 4 HOURS/NIGHT. 81 CONSTRUCTION DAYS
[11 empty] | 4 | 11 | [9 empty] | 176 | [6 empty] | 2
[11 empty] | 7 | 11 | [9 empty] | 308 | [6 empty] | 3
[11 empty] | 2 | 23 | [9 empty] | 184 | [6 empty] | 4
| 0102 60 |  | WORK ZONE SIGN |  |  |  | ED |  |  |  | 75 | 90 | [9 empty] | 6750 |  | 20475 |  |  |  |  | 1
[11 empty] | 70 | 45 | [9 empty] | 3150 | [6 empty] | 2
[11 empty] | 95 | 45 | [9 empty] | 4275 | [6 empty] | 3
[11 empty] | 70 | 90 | [9 empty] | 6300 | [6 empty] | 4
| 0102 71 13 |  | TEMPORARY BARRIER, F&I, LOW PROFILE, CONCRETE |  |  |  | LF | [14 empty] | 306 |  | 306 |  |  |  |  | 1
| 0102 71 23 |  | TEMPORARY BARRIER, RELOCATE, LOW PROFILE CONCRETE |  |  |  | LF | [14 empty] | 193 |  | 193 |  |  |  |  | 1
| 0102 74 1 |  | CHANNELIZING DEVICE- TYPES I, II, DI, VP, DRUM, OR LCD |  |  |  | ED |  |  |  | 532 | 90 | [9 empty] | 47880 |  | 109260 |  |  |  |  | 1
[11 empty] | 386 | 45 | [9 empty] | 17370 | [6 empty] | 2
[11 empty] | 206 | 45 | [9 empty] | 9270 | [6 empty] | 3
[11 empty] | 386 | 90 | [9 empty] | 34740 | [6 empty] | 4
| 0102 76 |  | ARROW BOARD / ADVANCE WARNING ARROW PANEL |  |  |  | ED |  |  |  | 4 | 90 | [9 empty] | 360 |  | 1125 |  |  |  |  | 1
[11 empty] | 6 | 45 | [9 empty] | 270 | [6 empty] | 2
[11 empty] | 3 | 45 | [9 empty] | 135 | [6 empty] | 3
[11 empty] | 4 | 90 | [9 empty] | 360 | [6 empty] | 4
| 0102 99 |  | PORTABLE CHANGEABLE MESSAGE SIGN, TEMPORARY |  |  |  | ED |  |  |  | 2 | 104 | [9 empty] | 208 |  | 658 |  |  |  |  | 1 | [9 empty] | 14 DAYS PRIOR TO CONSTRUCTION
[11 empty] | 2 | 45 | [9 empty] | 90 | [6 empty] | 2
[11 empty] | 4 | 45 | [9 empty] | 180 | [6 empty] | 3
[11 empty] | 2 | 90 | [9 empty] | 180 | [6 empty] | 4
| 0102 115 |  | TYPE III BARRICADE |  |  |  | ED |  |  |  | 10 | 90 | [9 empty] | 900 |  | 4095 |  |  |  |  | 1
[11 empty] | 20 | 45 | [9 empty] | 900 | [6 empty] | 2
[11 empty] | 11 | 45 | [9 empty] | 495 | [6 empty] | 3
[11 empty] | 20 | 90 | [9 empty] | 1800 | [6 empty] | 4
| 0706 1 3 |  | RAISED PAVEMENT MARKER, TYPE B |  |  |  | EA | [14 empty] | 930 |  | 5481 |  |  |  |  | 1
[22 empty] | 1715 | [6 empty] | 2
[22 empty] | 1041 | [6 empty] | 3
[22 empty] | 1795 | [6 empty] | 4
| 0710 11 101 |  | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID, 6" |  |  |  | GM | [14 empty] | 1.6643 |  | 7.8387 |  |  |  |  | 1
[22 empty] | 1.8848 | [6 empty] | 2
[22 empty] | 2.0976 | [6 empty] | 3
[22 empty] | 2.192 | [6 empty] | 4
| 0710 11 131 |  | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SKIP, 10-30 OR 3-9 SKIP, 6" WIDE |  |  |  | GM | [14 empty] | 0.1972 |  | 0.1972 |  |  |  |  | 1
| 0710 11 141 |  | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, 2-4 DOTTED GUIDELINE/ 6-10 DOTTED EXTENSION, 6" |  |  |  | GM | [14 empty] | 0.0638 |  | 0.0638 |  |  |  |  | 1
| 0710 11 201 |  | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, SOLID, 6" |  |  |  | GM | [14 empty] | 0.1068 |  | 1.251 |  |  |  |  | 1
[22 empty] | 0.0848 | [6 empty] | 2
[22 empty] | 0.5297 | [6 empty] | 3
[22 empty] | 0.5297 | [6 empty] | 4

## Sheet2
Summary of Temporary Traffic Control Plan Items
Section | Pay Item Number | Label | Pay Item Description | Max. Maint. Size | Structure Type | Structure Usage | Unit of Measure | Work Zone Speed (MPH) | Test Level (TL-2 or TL-3) | Existing (E) or Temp/New (T) | Number Required | Duration (Days) | Frequency (Days) | Length (FT) | Length Restriction (FT) | Width (FT) | Width of Barrier (IN) | Width of Hazard (IN) | Thickness (IN) | Cycles | Quantity |  |  | Total Quantity |  | Secondary Quantity |  |  | Location | [9 empty] | Design Notes | Construction Remarks
[21 empty] | AC/ Cycle | P | F | P | F | Unit | P | F | Const. Phase | Wall No. | Site No. | Alignment | Begin Station | End Station | Location Description | Offset | Side | Element ID

## Sheet3
Summary of Temporary Traffic Control Plan Items
Section | Pay Item Number | Label | Pay Item Description | Max. Maint. Size | Structure Type | Structure Usage | Unit of Measure | Work Zone Speed (MPH) | Test Level (TL-2 or TL-3) | Existing (E) or Temp/New (T) | Number Required | Duration (Days) | Frequency (Days) | Length (FT) | Length Restriction (FT) | Width (FT) | Width of Barrier (IN) | Width of Hazard (IN) | Thickness (IN) | Cycles | Quantity |  |  | Total Quantity |  | Secondary Quantity |  |  | Location | [9 empty] | Design Notes | Construction Remarks
[21 empty] | AC/ Cycle | P | F | P | F | Unit | P | F | Const. Phase | Wall No. | Site No. | Alignment | Begin Station | End Station | Location Description | Offset | Side | Element ID

## Sheet4
Summary of Temporary Traffic Control Plan Items
Section | Pay Item Number | Label | Pay Item Description | Max. Maint. Size | Structure Type | Structure Usage | Unit of Measure | Work Zone Speed (MPH) | Test Level (TL-2 or TL-3) | Existing (E) or Temp/New (T) | Number Required | Duration (Days) | Frequency (Days) | Length (FT) | Length Restriction (FT) | Width (FT) | Width of Barrier (IN) | Width of Hazard (IN) | Thickness (IN) | Cycles | Quantity |  |  | Total Quantity |  | Secondary Quantity |  |  | Location | [9 empty] | Design Notes | Construction Remarks
[21 empty] | AC/ Cycle | P | F | P | F | Unit | P | F | Const. Phase | Wall No. | Site No. | Alignment | Begin Station | End Station | Location Description | Offset | Side | Element ID